## Project
PROJECT INPUT
Yellow = mandatory (blue text = you type) ¦ Grey = optional ¦ Green = automatic. Row 5-6 and the example rows hold sample data: overwrite them.
Project name | Building project (sample) |  | Project size tier | Medium
Start date | 2026-10-20 |  | Direct worker cap (optional)
Finish date | 2028-02-24 |  | Notes | Tier: Small, Medium, Large or Mega. Leave the cap empty to use the tier.
Overall duration (days) | 493 | Calculated: finish - start + 1 (calendar days) | Parallel WBS level (optional)
1 = the Level 1 items work side by side (default). Use 2 if Level 1 is the whole site and Level 2 holds the buildings that run in parallel.
Milestones (optional)
Milestone name | Date
Foundation complete | 2027-04-29
Handover | 2028-02-24

## WBS
WBS: list areas in construction order (top row = first)
Fill the levels from the left, up to Level 5, and leave the levels you do not need blank. Level 1 is the block or building: blocks run in parallel, and the rows under the same Level 1 follow the order you list them. Names only, no codes.
Example with five levels: Tower 1 ¦ Block A ¦ Floor 3 ¦ Zone B ¦ Room 5. Each row is one area that BOQ lines can be assigned to.
Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | WBS Name (auto, used in BOQ dropdown)
Block A | Foundation |  |  |  | Block A - Foundation
Block A | Ground Floor |  |  |  | Block A - Ground Floor
Block A | First Floor |  |  |  | Block A - First Floor
Block B | Foundation |  |  |  | Block B - Foundation
Block B | Ground Floor |  |  |  | Block B - Ground Floor
Block B | First Floor |  |  |  | Block B - First Floor

## BOQ
BILL OF QUANTITIES
Pick the WBS from the dropdown (column G). Amount is calculated as Qty x Rate (you may overwrite it with the BOQ amount).
Item | Description | Unit | Qty | Rate | Amount | WBS | BOQ total | 3846200
2.1 | Excavation for foundations | m3 | 900 | 12 | 10800 | Block A - Foundation
2.2 | Blinding concrete 50mm | m3 | 60 | 380 | 22800 | Block A - Foundation
2.3 | Reinforcement steel bars, supply and fix | ton | 45 | 3200 | 144000 | Block A - Foundation
2.4 | RC footing, grade C40 concrete | m3 | 350 | 420 | 147000 | Block A - Foundation
2.5 | Backfilling and compaction | m3 | 500 | 25 | 12500 | Block A - Foundation
3.1 | Blockwork 200mm thick, hollow concrete | m2 | 6000 | 45 | 270000 | Block A - Ground Floor
3.2 | Cement plastering internal walls | m2 | 9000 | 28 | 252000 | Block A - Ground Floor
4.1 | Supply and install HVAC ductwork | m2 | 2500 | 160 | 400000 | Block A - Ground Floor
4.2 | Fire fighting sprinkler pipework | m | 3000 | 55 | 165000 | Block A - Ground Floor
4.3 | LV power cables and conduits | m | 12000 | 18 | 216000 | Block A - Ground Floor
5.1 | Carpet tiles, supply and lay | m2 | 2200 | 85 | 187000 | Block A - First Floor
5.2 | Emulsion paint to walls | m2 | 8000 | 12 | 96000 | Block A - First Floor
5.3 | Backfilling and compaction | m3 | 500 | 25 | 12500 | Block B - Foundation
5.4 | Blockwork 200mm thick, hollow concrete | m2 | 6000 | 45 | 270000 | Block B - Ground Floor
5.5 | Cement plastering internal walls | m2 | 9000 | 28 | 252000 | Block B - Ground Floor
5.6 | Supply and install HVAC ductwork | m2 | 2500 | 160 | 400000 | Block B - Ground Floor
5.7 | Fire fighting sprinkler pipework | m | 3000 | 55 | 165000 | Block B - Ground Floor
5.8 | LV power cables and conduits | m | 12000 | 18 | 216000 | Block B - Ground Floor
5.9 | Carpet tiles, supply and lay | m2 | 2200 | 85 | 187000 | Block B - First Floor
5.10 | Emulsion paint to walls | m2 | 8000 | 12 | 96000 | Block B - First Floor
5.11 | Excavation for foundations | m3 | 900 | 12 | 10800 | Block B - Foundation
5.12 | Blinding concrete 50mm | m3 | 60 | 380 | 22800 | Block B - Foundation
5.13 | Reinforcement steel bars, supply and fix | ton | 45 | 3200 | 144000 | Block B - Foundation
5.14 | RC footing, grade C40 concrete | m3 | 350 | 420 | 147000 | Block B - Foundation

## Holidays
Holidays
List every day that is not worked: public holidays, Eid, site closures. One date per row. The schedule skips these days, and they are written into the P6 calendar.
Days with shortened hours, such as Ramadan, are not supported yet: list full days off only. Leave this sheet empty if there are none.
Date | Description