## Project
PROJECT INPUT
Yellow = mandatory (blue text = you type) ¦ Grey = optional ¦ Green = automatic. Row 5-6 and the example rows hold sample data: overwrite them.
Project name |  |  | Project size tier
Start date |  |  | Direct worker cap (optional)
Finish date |  |  | Notes | Tier: Small, Medium, Large or Mega. Leave the cap empty to use the tier.
Overall duration (days) |  | Calculated: finish - start + 1 (calendar days) | Parallel WBS level (optional)
1 = the Level 1 items work side by side (default). Use 2 if Level 1 is the whole site and Level 2 holds the buildings that run in parallel.
Milestones (optional)
Milestone name | Date

## WBS
WBS: list areas in construction order (top row = first)
Fill the levels from the left, up to Level 5, and leave the levels you do not need blank. Floor share (%) and Zone share (%) are optional: leave them blank and the engine divides the work equally, between the floors and between the zones of each floor. To change it, type percentages, for example 30, 25, 20, 15, 10 for five zones. Works (optional) is Substructure, Floor, Roof or External; if it is blank, it is read from the names (Foundation, Roof, ...). In the sample, Level 1 is the whole site, Level 2 the block (Parallel WBS level 2), Level 3 the part, Level 4 the floor and Level 5 the zone.
Example with five levels: Tower 1 ¦ Block A ¦ Floor 3 ¦ Zone B ¦ Room 5. Each row is one area that BOQ lines can be assigned to.
Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | WBS Name (auto, used in BOQ dropdown) | Floor share (%) | Zone share (%) | Works (optional)

## BOQ
BILL OF QUANTITIES
Paste the BOQ lines as they are, or create this workbook from a client BOQ on the Run the engine page. In column G enter the building the line belongs to (for example "Block A"); leave it empty to spread a line over every row of the WBS sheet. Amount is calculated as Qty x Rate (you may overwrite it with the BOQ amount).
Item | Description | Unit | Qty | Rate | Amount | WBS | BOQ total

## Holidays
Holidays
List every day that is not worked: public holidays, Eid, site closures. One date per row. The schedule skips these days, and they are written into the P6 calendar.
Days with shortened hours, such as Ramadan, are not supported yet: list full days off only. Leave this sheet empty if there are none.
Date | Description